## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MoSCoW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-001 | As a User, I want to login securely. | Must Have | None | Developer | Done
Sprint 1 | Sprint 1 | US-002 | As a Guest, I want to create a new account. | Must Have | None | Developer | Done
Sprint 1 | Sprint 1 | US-003 | As a Staff, I want to add products to inventory. | Must Have | US-001 | Developer | Done
Sprint 1 | Sprint 1 | US-004 | As a Staff, I want to view all products. | Must Have | US-003 | Developer | Done
Sprint 1 | Sprint 1 | US-005 | As a Staff, I want to update product stock. | Must Have | US-004 | Developer | Done
Sprint 1 | Sprint 1 | US-006 | As an Admin, I want to delete old products. | Should Have | US-004 | Developer | Done
Sprint 1 | Sprint 1 | US-007 | As a Staff, I want to search products easily. | Could Have | US-004 | Developer | Done
Sprint 2 | Sprint 2 | US-008 | As an Admin, I want to view store value. | Should Have | None | Developer | Done
Sprint 2 | Sprint 2 | US-009 | As an Admin, I want to see staff count. | Should Have | US-010 | Developer | Done
Sprint 2 | Sprint 2 | US-010 | As an Admin, I want to view employees. | Should Have | US-001 | Developer | Done
Sprint 2 | Sprint 2 | US-011 | As an Admin, I want to remove staff access. | Should Have | US-010 | Developer | Done
Sprint 2 | Sprint 2 | US-012 | As an Admin, I want to add suppliers. | Must Have | None | Developer | Done
Sprint 2 | Sprint 2 | US-013 | As a Staff, I want to view supplier details. | Must Have | US-012 | Developer | Done
Sprint 2 | Sprint 2 | US-014 | As an Admin, I want to update suppliers. | Must Have | US-012 | Developer | Done
Sprint 2 | Sprint 2 | US-015 | As an Admin, I want to delete suppliers. | Must Have | US-012 | Developer | Done
Sprint 3 | Sprint 3 | US-016 | As a Staff, I want to create purchase orders. | Must Have | US-013 | Developer | Done
Sprint 3 | Sprint 3 | US-017 | As a Staff, I want to update purchase orders. | Must Have | US-016 | Developer | Done
Sprint 3 | Sprint 3 | US-018 | As a Staff, I want to receive supplier stock. | Must Have | US-016 | Developer | Done
Sprint 3 | Sprint 3 | US-019 | As a Staff, I want to record damaged stock. | Should Have | US-018 | Developer | Done
Sprint 3 | Sprint 3 | US-020 | As an Admin, I want to return damaged stock. | Should Have | US-019 | Developer | Done
Sprint 3 | Sprint 3 | US-021 | As a Staff, I want to track stock movement. | Must Have | US-004 | Developer | Done
Sprint 3 | Sprint 3 | US-022 | As an Admin, I want inventory value reports. | Should Have | US-021 | Developer | Done
Sprint 4 | Sprint 4 | US-023 | As an Admin, I want to set reorder levels. | Must Have | US-004 | Developer | Done
Sprint 4 | Sprint 4 | US-024 | As a Staff, I want to track expired items. | Must Have | US-004 | Developer | Done
Sprint 4 | Sprint 4 | US-025 | As a Staff, I want to view transactions. | Must Have | US-021 | Developer | Done
Sprint 4 | Sprint 4 | US-026 | As a Staff, I want to export inventory data. | Could Have | US-004 | Developer | Done
Sprint 4 | Sprint 4 | US-027 | As an Admin, I want to import product data. | Should Have | US-003 | Developer | Done
Sprint 4 | Sprint 4 | US-028 | As a Staff, I want barcode scanning support. | Should Have | US-003 | Developer | Done
Sprint 4 | Sprint 4 | US-029 | As a Staff, I want to add product images. | Could Have | US-003 | Developer | Done
Sprint 4 | Sprint 4 | US-030 | As an Admin, I want sales reports. | Should Have | US-004 | Developer | Done
Sprint 4 | Sprint 4 | US-031 | As a Staff, I want to track customer orders. | Must Have | US-004 | Developer | Done
Sprint 4 | Sprint 4 | US-032 | As a Staff, I want to manage returns. | Must Have | US-031 | Developer | Done
Sprint 4 | Sprint 4 | US-033 | As an Admin, I want to issue invoices. | Must Have | US-031 | Developer | Done
Sprint 4 | Sprint 4 | US-034 | As a System, I want low stock alerts. | Should Have | US-019 | System | Done
Sprint 5 | Sprint 5 | US-035 | As a User, I want login authentication. | Must Have | None | System | Done
Sprint 5 | Sprint 5 | US-036 | As a User, I want password recovery. | Must Have | US-035 | System | Done
Sprint 5 | Sprint 5 | US-037 | As a User, I want session control. | Must Have | US-035 | System | Done
Sprint 5 | Sprint 5 | US-038 | As an Admin, I want audit logs. | Should Have | US-021 | Developer | Done
Sprint 5 | Sprint 5 | US-039 | As an Admin, I want role updates. | Could Have | US-010 | Developer | Done
Sprint 5 | Sprint 5 | US-040 | As an Admin, I want inventory dashboard. | Must Have | US-004 | Developer | Done
Sprint 5 | Sprint 5 | US-041 | As an Admin, I want monthly reports. | Should Have | US-022 | Developer | Done
Sprint 5 | Sprint 5 | US-042 | As an Admin, I want product trends. | Should Have | US-022 | Developer | Done
Sprint 5 | Sprint 5 | US-043 | As a System, I want notification settings. | Could Have | US-034 | System | Done
Sprint 5 | Sprint 5 | US-044 | As an Admin, I want supplier export. | Should Have | US-013 | Developer | Done
Sprint 5 | Sprint 5 | US-045 | As an Admin, I want supplier import. | Should Have | US-012 | Developer | Done
Sprint 5 | Sprint 5 | US-046 | As a System, I want automated backups. | Must Have | None | System | To Do
Sprint 5 | Sprint 5 | US-047 | As an Admin, I want restore backups. | Must Have | US-046 | Developer | To Do
Sprint 5 | Sprint 5 | US-048 | As a System, I want mobile support. | Could Have | US-040 | System | To Do
Sprint 5 | Sprint 5 | US-049 | As a Staff, I want advanced search. | Could Have | US-007 | Developer | To Do
Sprint 5 | Sprint 5 | US-050 | As an Admin, I want audit reports | Should Have | US-038 | Developer | To Do
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7