## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Tester | 15-Oct | Login page validation failed for empty inputs | Sprint 1 | Frontend Dev | UI Bug | Added proper input validation and error messages | 17-Oct | Closed | Working as expected
2 | Tester | 18-Oct | Admin unable to add new products | Sprint 1 | Backend Dev | Functional | Fixed API issue and validated request body | 20-Oct | Closed | Product added successfully
3 | Tester | 22-Oct | Product list not loading on refresh | Sprint 1 | Full Stack Dev | Functional | Corrected API call and state handling | 24-Oct | Closed | Issue resolved
4 | Tester | 26-Oct | Stock quantity not updating after sales | Sprint 2 | Backend Dev | Logic Error | Updated stock update logic in database | 28-Oct | Closed | Stock updates correctly
5 | Tester | 30-Oct | Duplicate product IDs allowed | Sprint 2 | Backend Dev | Data Integrity | Added unique constraint and validation | 02-Nov | Closed | Duplicate entries prevented
6 | Tester | 05-Nov | Search functionality not returning results | Sprint 2 | Frontend Dev | Functional | Fixed search filter logic | 07-Nov | Closed | Search works properly
7 | Tester | 10-Nov | Pagination not working in inventory list | Sprint 3 | Frontend Dev | UI Bug | Implemented proper pagination logic | 12-Nov | Closed | Pagination working
8 | Tester | 15-Nov | Staff role accessing admin features | Sprint 3 | Backend Dev | Security | Fixed role-based access control | 18-Nov | Closed | Access restricted correctly
9 | Tester | 20-Nov | Low stock alert not triggering | Sprint 3 | Backend Dev | Functional | Implemented threshold-based alert logic | 22-Nov | Closed | Alerts triggered correctly
10 | Tester | 25-Nov | Reports page loading slowly | Sprint 4 | Full Stack Dev | Performance | Optimized database queries | 28-Nov | Closed | Performance improved
11 | Tester | 28-Nov | Product image upload failed | Sprint 4 | Frontend Dev | UI Bug | Fixed file upload validation | 30-Nov | Closed | Image upload works
12 | Tester | 01-Dec | Incorrect total stock value in dashboard | Sprint 4 | Backend Dev | Calculation Error | Corrected aggregation logic | 03-Dec | Closed | Dashboard accurate
13 | Tester | 02-Dec | CSV import missing some products | Sprint 4 | Backend Dev | Data Issue | Fixed CSV parser logic | 04-Dec | Closed | All products imported
14 | Tester | 03-Dec | Export inventory report incorrect format | Sprint 4 | Frontend Dev | UI Bug | Corrected export formatting | 05-Dec | Closed | Report format correct
15 | Tester | 05-Dec | Unauthorized user accessing staff page | Sprint 4 | Backend Dev | Security | Added route-level authorization | 07-Dec | Closed | Access controlled
16 | Tester | 06-Dec | Product delete not reflected immediately | Sprint 5 | Frontend Dev | Functional | Refreshed UI after delete action | 08-Dec | Closed | UI synced properly
17 | Tester | 07-Dec | Inventory dashboard charts not loading | Sprint 5 | Frontend Dev | UI Bug | Fixed chart data binding | 09-Dec | Closed | Charts displayed
18 | Tester | 08-Dec | Order placement not reducing stock | Sprint 5 | Backend Dev | Logic Error | Linked order and stock update logic | 10-Dec | Closed | Stock reduced correctly
19 | Tester | 09-Dec | Session timeout not working | Sprint 5 | Backend Dev | Security | Configured session expiry properly | 11-Dec | Closed | Session expires correctly
20 | Tester | 10-Dec | Logout not clearing session | Sprint 5 | Backend Dev | Security | Fixed session destroy logic | 12-Dec | Closed | Session cleared
21 | Tester | 10-Dec | Product category filter not working | Sprint 5 | Frontend Dev | Functional | Fixed filter conditions | 12-Dec | Closed | Filter works
22 | Tester | 11-Dec | Incorrect supplier details displayed | Sprint 5 | Backend Dev | Data Issue | Corrected supplier mapping | 13-Dec | Closed | Correct data shown
23 | Tester | 11-Dec | Stock adjustment feature crashing | Sprint 5 | Backend Dev | Runtime Error | Handled null values properly | 13-Dec | Closed | Feature stable
24 | Tester | 12-Dec | Notification count incorrect | Sprint 5 | Backend Dev | Logic Error | Updated notification calculation | 14-Dec | Closed | Count accurate
25 | Tester | 12-Dec | Add supplier form missing validations | Sprint 5 | Frontend Dev | UI Bug | Added mandatory field validation | 14-Dec | Closed | Form validated
26 | Tester | 13-Dec | Admin dashboard summary mismatch | Sprint 5 | Backend Dev | Calculation Error | Fixed summary queries | 14-Dec | Closed | Summary accurate
27 | Tester | 13-Dec | Staff unable to view assigned products | Sprint 5 | Backend Dev | Functional | Fixed role-product mapping | 14-Dec | Closed | Staff view enabled
28 | Tester | 13-Dec | Search performance slow for large data | Sprint 5 | Backend Dev | Performance | Added indexing in database | 14-Dec | Closed | Search optimized
29 | Tester | 14-Dec | UI misalignment on mobile view | Sprint 5 | Frontend Dev | UI Bug | Applied responsive CSS fixes | 14-Dec | Closed | Mobile responsive
30 | Tester | 14-Dec | Order history not loading | Sprint 5 | Backend Dev | Functional | Fixed API response issue | 14-Dec | Closed | Order history visible
31 | Tester | 14-Dec | Broken links in footer | Sprint 5 | Frontend Dev | UI Bug | Updated route links | 14-Dec | Closed | Links working
32 | Tester | 14-Dec | Incorrect date format in reports | Sprint 5 | Frontend Dev | UI Bug | Standardized date formatting | 14-Dec | Closed | Date format fixed
33 | Tester | 15-Dec | Duplicate notifications shown | Sprint 5 | Backend Dev | Logic Error | Removed redundant trigger | 15-Dec | Closed | Duplicates removed
34 | Tester | 15-Dec | User profile update failing | Sprint 5 | Backend Dev | Functional | Fixed update API logic | 15-Dec | Closed | Profile updated
35 | Tester | 15-Dec | System logs not generated | Sprint 5 | Backend Dev | Functional | Enabled logging service | 15-Dec | Closed | Logs generated
36 | Tester | 15-Dec | Error messages unclear to users | Sprint 5 | Frontend Dev | UI Improvement | Improved error message text | 15-Dec | Closed | User-friendly messages
37 | Tester | 15-Dec | Inventory sync delay | Sprint 5 | Backend Dev | Performance | Optimized background jobs | 15-Dec | Closed | Sync faster
38 | Tester | 15-Dec | Role permissions mismatch | Sprint 5 | Backend Dev | Security | Corrected permission matrix | 15-Dec | Closed | Permissions correct
39 | Tester | 15-Dec | Final UAT feedback issues | Sprint 5 | Team | Testing | Resolved minor UI and flow issues | 15-Dec | Closed | UAT approved
40 | Tester | 15-Dec | Deployment checklist issues | Sprint 5 | Team | Process | Completed deployment validations | 15-Dec | Closed | System ready
41 | Tester | 16-Oct | User registration form missing mandatory validation | Sprint 1 | Frontend Dev | UI Bug | Added required field validation | 18-Oct | Closed | Validation working
42 | Tester | 18-Oct | Incorrect error message shown for invalid login | Sprint 1 | Frontend Dev | UI Bug | Updated error handling logic | 20-Oct | Closed | Error message correct
43 | Tester | 22-Oct | Role selection not saved during user creation | Sprint 1 | Backend Dev | Functional | Fixed role mapping logic | 24-Oct | Closed | Roles saved properly
44 | Tester | 27-Oct | Product category not displayed in product list | Sprint 2 | Backend Dev | Data Issue | Corrected category join query | 29-Oct | Closed | Category visible
45 | Tester | 30-Oct | Stock history not recorded for updates | Sprint 2 | Backend Dev | Functional | Implemented stock audit trail | 02-Nov | Closed | History maintained
46 | Tester | 05-Nov | Advanced search filters not applied | Sprint 3 | Frontend Dev | Functional | Fixed filter parameter binding | 07-Nov | Closed | Filters working
47 | Tester | 12-Nov | Low stock threshold not configurable | Sprint 3 | Backend Dev | Functional | Added admin-configurable threshold | 14-Nov | Closed | Threshold configurable
48 | Tester | 22-Nov | Dashboard summary cards not refreshing | Sprint 4 | Frontend Dev | UI Bug | Triggered data reload on update | 24-Nov | Closed | Dashboard refreshed
49 | Tester | 02-Dec | Monthly inventory report totals incorrect | Sprint 4 | Backend Dev | Calculation Error | Fixed monthly aggregation logic | 04-Dec | Closed | Totals accurate
50 | Tester | 12-Dec | Final regression issues in inventory workflow | Sprint 5 | Team | Testing | Resolved workflow and UI issues | 14-Dec | Closed | System stable

## Sheet2
Logical
User Interface
Maintainability
Standards
Others